## OVERVIEW
Eleven stages in the solution-development process è | 1. Business Mission, Vision, Strategy & Goals | 2. Business Process & Requirements | 3. User Requirements | 4. Functional Requirements | 5. Non-Functional Requirements (NFR) | 6. Solution Analysis | 7. Solution Design | 8. Solution Construction | 9. Testing | 10. Documentation | 11. Training
| ç---------------------Planning (WHY & WHEN) and Analysis (WHAT)------------------------------------------è |  |  |  |  | ç--------------------- Solution Development (H O W)--------------------è |  |  |  | ç--Implementation & Transition--è. . .
PROGRESSIVE and ITERATIVE ACTIVITIES... | Articulate clear direction at the enterprise or business unit level. | Identify clear business-level performance improvements via gap analysis of the AS-IS vs. TO-BE. | Determine what improvements users need from individual business processes and systems (AS-IS vs. TO-BE). | Determine the needed operational behavior of improved business processes and systems. | Specify anything that enhances the success and value of project deliverables to the users. | Convert requirements to solution specifications. | Develop the complete technical details for preliminary logical and functional designs and for final design and construction. | Build the complete technical solution. | Plan and conduct Unit, String, System, and Usability testing. | Develop and deliver user- and support-oriented documentation. | Develop and deliver user- and support-oriented instruction.
[KEY ROLES]: ORGANIZE/OVERSEE APPROVE/AUTHORIZE PERFORM/PRODUCE SUPPORT | Business Sponsor [A] Bus Process Expert [P] | Business Sponsor [A] Bus Process Expert [P] | Bus Process Expert [P] | Bus Process Expert [S] | Bus Process Expert [S] |  |  |  | Bus Process Expert [P] | Bus Process Expert [P] | Bus Process Expert [P]
| Strategic Marketing [S] Product R&D [S] | Strategic Marketing [P] Product R&D [P] | Strategic Marketing [P] Product R&D [P] | Strategic Marketing [S] Product R&D [P] | Product R&D [P] | Product R&D [P] |  |  | Strategic Marketing [P] | Strategic Marketing [P] | Strategic Marketing [P]
| Business Analysis [S] | Business Analysis [P] | Business Analysis [P] | Business Analysis [P] | Business Analysis [P] | Bus Sys Anlyst [P] | Bus Sys Anlyst [S] | Bus Sys Anlyst [S] | Business Analysis [S] Bus Sys Anlyst [S] | Business Analysis [S] | Business Analysis [S]
| IT Architecture [S] IT Development [S] IT DBMS [S] | IT Architecture [S] IT Development [S] IT DBMS [S] | IT Architecture [S] IT Development [S] IT DBMS [S] | IT Architecture [P] IT Development [P] IT DBMS [S] | IT Architecture [P] IT Development [P] IT DBMS [S] | IT Architecture [P] IT Development [P] IT DBMS [P] | IT Architecture [P] IT Development [P] IT DBMS [P] | IT Architecture [S] IT Development [P] IT DBMS [P] | IT Architecture [S] IT Development [P] IT DBMS [P] | IT Architecture [S] IT Development [S] | IT Architecture [S] IT Development [S]
| IT Infrastructure [S] | IT Infrastructure [S] | IT Infrastructure [S] | IT Infrastructure [S] QA [S] | IT Infrastructure [P] QA [S] | IT Infrastructure [P] QA [P] Sys Analyst [P] | IT Infrastructure [P] QA [P] Sys Analyst [P] | IT Infrastructure [P] QA [P] Sys Analyst [P] | IT Infrastructure [P] QA [P] Sys Analyst [P]
|  |  | End User [S] | End User [S] |  |  |  |  | End User [S] | End User [S] | End User [S]
[10 empty] | Help Desk [S] | Help Desk [S]
| Finance [S] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [S] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [S] Procurement [S] | Finance [S] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [S] Marketing [S] Training [S] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [P] Marketing [P] Training [P] Procurement [S] | Finance [P] Legal/Regulatory/ Compliance [S] Marketing [P] Training [P] Procurement [S]
| Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O] | Project Mgmt [O]
| Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O] | Program Mgmt [O]
PMI PMBOK Process Correlation | INITIATE | PLAN (incl. analysis) |  |  |  | EXECUTE, MONITOR, CONTROL
Key Deliverables | Business Case, CBA, Charter | Statement of Work |  |  |  | Statement of Work
IIBA BABOK Knowledge Areas Correlation | Enterprise Analysis | Business Analysis Planning & Monitoring Requirements Elicitation and Analysis Requirements Management and Communication |  |  |  | Solution Assessment and Validation |  |  | Requirements Management and Communication
Requirements Management and Communication
Agile Correlation | Envision Product, Capture User Stories/Features, Prioritize Features, Plan Iterations & Releases D |  |  |  |  | D | Conduct Iterations and Releases
INPUTS | Business Case. Cost-Benefit Analysis. | Requirements Work Plan (high-level). | System Use Case models. | System Use Case models. | NFR List • Response time • Backup frequency • Security levels • Disaster recovery | User experience conceptual model. | Data maps. Data flow diagrams. | Pseudo code. | Use Cases. | Document Index & Repository. | Training Plan. Modes and Audiences.
| Roadmap. Business Capabilities Summary. | Context & relationship models. | Activity Diagrams. Screen concepts. Use case outline & inventory. | Activity Diagrams. Screen concepts. |  | Screen mockups (high-level). | Test analysis & design detail. Data report design. |  |  | Transition Requirements – e.g., processes, staffing, training, and skills needed for successful deployment into production. | Transition Requirements – e.g., processes, staffing, training, and skills needed for successful deployment into production.
|  | Business process models. |  |  |  | Test analysis & design plan.
|  | Business rules. Business use case models. | Transition Requirements (high-level). Reporting requirements (high-level). |  |  | IT Architecture Design (logical). Data Models (e.g., Business Object Model, ERDs, state and class diagrams). DBMS & System Interfaces (high-level).
Organizational change requirements.
OUTPUTS | Charter. | Requirements Work Plan (refined). | System Use Case narratives (actor side). Activity Diagrams (refined). Transition requirements (detailed). Reporting requirements (detailed). | System Use Case narratives (system side). Activity Diagrams (refined). Content Matrix. Data for reporting requirements (detailed). Feature specifications. |  | Modified Use cases & ADs. Processing rules. Functional specs: - UX design. - User Interface rules. - Screen mockups (detailed). - Metadata. Data elements & diagrams. DBMS & system interfaces (detailed). Transitional requirements. Cross-application dependencies. | Content Matrix (finalized). IT Arch Design (physical). | Program code. Data report construction. | Test Scenarios. Test Cases. Test Scripts. Report Testing. Financial Testing. |  | Training scripts.
Feature Specifications.
|  | Business Rqmts Doc (BRD) è | Business Rqmts Doc (BRD) è | Business Rqmts Doc (BRD) è | Business Rqmts Doc (BRD) | Solution Rqmts Document (SRD) | Solution Design Document (SDD) | Solution Design Document (SDD)
è
NOTE that some KEY ROLES may include individuals from more than one area. For example, the categories Bus Process Expert amd End User can/should include representatives from production/operations, customers (internal & external), contributing consultants, etc.

## PROJECT PLAN template
'% Complete | WBS | TASK | Duration | Target Start | Actual Start | Target End | Actual End | Dependencies | Resources | NOTES
| 1 | INITIATE
| 1.1 | PLC Stage 1 - Business Mission, Vision, Strategy, Goals
| 1.11 | Business Case | [6 empty] | Bus Sponsor
| 1.12 | CBA | [6 empty] | Bus Sponsor
| 1.13 | Charter | [6 empty] | Bus Sponsor, PM
| 1.2 | Kickoff # 1 | [6 empty] | PM
| 2 | PLAN & ANALYZE
| 2.1 | Draft Statement of Work (SOW) | [6 empty] | PM
| 2.2 | Kickoff # 2 | [6 empty] | PM
| 2.3 | PLC Stage 2 - Business Processes & Requirements
| 2.31 | Context & Relationship Models | [6 empty] | BA, Bus SME
| 2.32 | Business Process Models | [6 empty] | BA, Bus SME
| 2.33 | Business Rules | [6 empty] | BA, Bus SME
| 2.34 | Business Use Case Models | [6 empty] | BA, Bus SME
| 2.35 | Organizational Change Requirements | [6 empty] | BA, Bus SME
| 2.36 | Business Rqmts Document (BRD) - gate 1 | [6 empty] | BA, PM
| 2.4 | PLC Stage 3 - User Requirements
| 2.41 | System Use Case models | [6 empty] | BA, Bus SME
| 2.42 | Activity Diagrams | [6 empty] | BA, Bus SME
| 2.43 | Screen Concepts | [6 empty] | BA, Bus SME
| 2.44 | Transition Requirements | [6 empty] | BA, Bus SME
| 2.45 | Reporting Requirements | [6 empty] | BA, Bus SME
| 2.46 | Business Rqmts Document (BRD) - gate 2 | [6 empty] | BA, PM
| 2.5 | PLC Stage 4 - Functional Requirements
| 2.51 | System Use Case models | [6 empty] | BA
| 2.52 | Activity Diagrams | [6 empty] | BA
| 2.53 | Screen Concepts | [6 empty] | BA
| 2.54 | Feature Specifications | [6 empty] | BA
| 2.55 | Business Rqmts Document (BRD) - gate 3 | [6 empty] | BA, PM
| 2.6 | PLC Stage 5 - Non-functional Requirements | [6 empty] | BA, PM
| 2.7 | BRD Final Signoff | [6 empty] | BA, PM
| 2.8 | SOW Gate Review | [6 empty] | PM
| 3 | EXECUTE, MONITOR, & CONTROL
| 3.1 | PLC Stage 6 - Solution Analysis
| 3.11 | Data Models | [6 empty] | IT Delivery Mgr
| 3.12 | Object Models (ERDs) | [6 empty] | IT Delivery Mgr
| 3.13 | System Interfaces | [6 empty] | IT Delivery Mgr
| 3.14 | Testing Strategy | [6 empty] | IT Delivery Mgr
| 3.15 | Functional Specifications | [6 empty] | IT Delivery Mgr
| 3.16 | Solution Requirements Document - gate 1 | [6 empty] | IT Delivery Mgr
| 3.17 | SOW Gate Review | [6 empty] | PM
| 3.2 | PLC Stage 7 - Solution Design
| 3.21 | Data Maps | [6 empty] | IT Architect, Del Mgr
| 3.22 | Data Flow Diagrams | [6 empty] | IT Architect, Del Mgr
| 3.23 | Testing - Analysis & Design | [6 empty] | Test Mgr
| 3.24 | Data Report Design | [6 empty] | IT Delivery Mgr
| 3.25 | Solution Requirements Document - gate 2 | [6 empty] | IT Architect, Del Mgr
| 3.26 | SOW Gate Review | [6 empty] | PM
| 3.3 | PLC Stage 8 - Solution Build
| 3.31 | Coding | [6 empty] | IT Delivery Mgr
| 3.32 | Data Report Build | [6 empty] | IT Delivery Mgr
| 3.33 | Solution Requirements Document - gate 3 | [6 empty] | IT Delivery Mgr
| 3.34 | SOW Gate Review | [6 empty] | PM
| 3.4 | PLC Stage 9 - Testing
| 3.41 | Unit Testing | [6 empty] | Testing Mgr
| 3.42 | String Testing | [6 empty] | Testing Mgr
| 3.43 | System Testing | [6 empty] | Testing Mgr
| 3.44 | User Acceptance Testing | [6 empty] | Testing Mgr, Bus SME
| 3.5 | PLC Stage 10 - Documentation
| 3.51 | Technical Documentation | [6 empty] | IT Delivery Mgr
| 3.52 | Internal User Documentation | [6 empty] | PM
| 3.53 | External User Documentation | [6 empty] | Business SME
| 3.6 | PLC Stage 11 - Training
| 3.61 | Internal Training | [6 empty] | Training Mgr
| 3.62 | External Training | [6 empty] | Training Mgr
| 3.7 | SOW Gate Review | [6 empty] | PM
| 3.8 | Progress Status Reports (recurring)
| 3.81 | Report # 1 | [6 empty] | PM
| 3.82 | Report # 2 | [6 empty] | PM
| 3.83 | Report # 3 | [6 empty] | PM
| 3.84 | Report # 4 | [6 empty] | PM
| 3.85 | Report # 5 | [6 empty] | PM
| 3.86 | Report # 6 | [6 empty] | PM
| 4 | CLOSE
| 4.1 | Lessons Learned | [6 empty] | PM
| 4.2 | Transition to Production (ownership transfer) | [6 empty] | PM
| 4.21 | Production team staffing | [6 empty] | Prodn Mgr
| 4.21 | Production team skills | [6 empty] | Prodn Mgr
| 4.21 | Production team training | [6 empty] | Prodn Mgr
| 4.21 | Support processes, procedures, staffing (incl. HelpDesk) | [6 empty] | Prodn Mgr
| 4.21 | Problem escalation processes, procedures, staffing | [6 empty] | Prodn Mgr
| 4.21 | Partner/vendor roles & responsibilities | [6 empty] | Prodn Mgr
| 4.3 | Post-Implementation Warranty/Stabilization period, roles, responsibilities | [6 empty] | PM
| 4.4 | Benefits Realization Review | [6 empty] | PM

## ROSTER template
Name | Title | Department (or Firm) | Area of Specialty | Role/ responsibility | Phone contact | Alternate | Alternate’s phone | Admin. Assistant
Business Sponsor
Business SME
Business Analyst
Product Research
Product Development
System Architect
Data Architect
IT Delivery Manager
Finance
Regulatory
Compliance
Legal
Program Manager
Project Manager
Procurement

## AGILE
A comparison and contrast of Agile vs. Traditional Project Management
Choosing between Agile and Traditional Project Management